## 21130445_Q&A_QuanLySanPham_EN
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | Add Product | SRS - Product Management | 1.0 | Basic Information product | In the form for adding basic information, when users want to upload an image, they have two options: a 1:1 ratio or a 3:4 ratio. However, I don't see any guidance or explanation about the differences between these ratios to help users make an informed choice. I think it would be helpful to have a button next to the options that users can click to display the guidance. Do you think this is the right approach? Please confirm. | Agreed, adding a small guide in the form of a tooltip or a button next to the image ratio options would help users better understand the differences between these choices. We will consider adding an icon that allows users to quickly access the explanation or notification. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
2 | Add Product | SRS - Product Management | 1.0 | Add Information product | In the product information input interface, there are too many attribute fields with various conditions, which can confuse first-time users. I think adding a small guide or checklist next to the form would help users easily follow along. Do you think this is the right approach? Please confirm. | Yes, the current product input interface has many required fields, which can be challenging for new users. We will consider adding a small guide or checklist next to the fields or on the side to help users easily follow the system's requirements. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
3 | Add Product | SRS - Product Management | 1.0 | Add image | In the product information input interface, only jpg, jpeg, and png file formats are supported for image uploads. But what will happen if users try to upload a file with a different format? I think there should be a popup notification informing users of the incorrect file format. Do you think this is the right approach? Please confirm. | Yes, when users upload a file with an invalid format, a warning popup should be displayed. This will help prevent unwanted errors and improve the user experience when entering product information. We will consider implementing this feature to best support our users. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
4 | Add Product | SRS - Product Management | 1.0 | Add video | In the step for adding a video to the product, there are constraints such as a maximum size of 30MB, a resolution not exceeding 1280x1280px, and a length of 10s to 60s. But what will happen if users upload a video that does not comply with these rules? I think we should allow users to edit the video directly on the website to meet the requirements, enhancing the user experience. Do you think this is the right approach? Please confirm. | Your suggestion is very helpful. Instead of only notifying users of an error when uploading an invalid video, we will consider adding a feature that allows users to edit the video directly on the website to comply with size and length requirements. This will significantly improve the user experience while minimizing errors during the upload process. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
5 | Add Product | SRS - Product Management | 1.0 | Add delivery information | In the step for adding packaging weight and dimensions, what happens if the product has variants with different sizes and weights? I think there should be an option to set weight and dimensions for each variant. Do you think this is the right approach? Please confirm. | This proposal makes sense. We will consider adding an option for users to set individual weight and dimensions for each product variant. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
6 | Product Management | SRS - Product Management | 1.0 | See list products | In the product list screen of the shop, while basic information about the products is displayed, it would be convenient for shop management if products were automatically evaluated by the system. I think there should be an additional quality assessment to provide feedback on whether the product listings need improvement and what specific improvements are necessary for better posts. Do you think this is the right approach? Please confirm. | Agreed, adding a content quality assessment feature will help the shop improve their listings. We will consider implementing this feature. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
7 | Add Product | SRS - Product Management | 1.0 | Thêm sản phẩm | The system currently has the feature to add one product at a time, but what if users have a bulk of products that need to be uploaded quickly? I think there should be an option for bulk product uploads. Users could download a template, fill it out according to the specified format, and then upload it for the system to process automatically. Do you think this is the right approach? Please confirm. | Agreed, this feature will help users save time when uploading multiple products. We will consider adding this functionality, including support for a template for bulk uploads. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
8 | Product Management | SRS - Product Management | 1.0 | Xem danh sách sản phẩm | In the shop's product list screen, by default, each product is displayed in a detailed vertical view, including all variants, which makes it hard to read. I think there should be a toggle option to switch to a buyer's view, displaying concise information for each product so that shops can quickly review multiple products at once. Do you think this is the right approach? Please confirm. | Agreed, adding a streamlined view will help shops manage their product lists more easily. We will consider implementing this feature. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
9 | Product Management | SRS - Product Management | 1.0 | Tồn kho sản phẩm | The system currently has a product inventory feature, but there are no reminders for low stock levels. I think users should have the option to enable notifications for low inventory when it falls below a certain threshold, allowing shops to proactively restock. Do you think this is the right approach? Please confirm. | Agreed, this feature will help shops proactively manage their inventory. We will consider adding this optional reminder function. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
10 | Add Product | SRS - Product Management | 1.0 | Thêm thông tin chi tiếtsản phẩm | In the product detail information interface, the current information form is fixed. I think it should be flexible and change based on the category selected in the "Basic Information" step to better suit each type of category. Do you think this is the right approach? Please confirm. | Agreed, having a flexible form that changes based on the category will help users input more relevant information. We will consider adding this feature to improve the user experience. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium

## 21130445_Q&A_QuanLySanPham_VN
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thông tin cơ bản | Trong form thêm thông tin cơ bản. Khi người dùng muốn thêm hình ảnh, họ sẽ có 2 options là tỉ lệ 1:1 hoặc 3:4. Nhưng tôi không thấy hướng dẫn, giải thích sự khác nhau giữa các tỉ lệ đó cho người dùng dễ dàng lựa chọn? Tôi nghĩ nên có một button bên cạnh để người dùng nhấn vào sẽ hiển thị hướng dẫn. Tôi nghĩ có đúng không? Xin vui lòng xác nhận | Đồng ý, việc thêm một hướng dẫn nhỏ dưới dạng tooltip hoặc một button cạnh các tùy chọn tỉ lệ hình ảnh sẽ giúp người dùng hiểu rõ sự khác nhau giữa các tùy chọn này. Chúng tôi sẽ xem xét thêm một biểu tượng giúp người dùng truy cập nhanh vào phần giải thích hoặc thông báo. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
2 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm thông tin sản phẩm | Trong giao diện thêm thông tin sản phẩm có quá nhiều trường thuộc tính cần nhập với các điều kiện khác nhau, dễ gây rối loạn cho người dùng lần đầu tiếp xúc. Tôi nghĩ nên thêm một bảng hướng dẫn nhỏ bên cạnh để người dùng dễ theo dõi và làm theo.Tôi nghĩ có đúng không? Xin vui lòng xác nhận | Đúng vậy, giao diện thêm sản phẩm hiện tại có nhiều trường yêu cầu nhập liệu, có thể gây khó khăn cho người mới. Chúng tôi sẽ xem xét bổ sung một bảng hướng dẫn nhỏ ở cạnh các trường hoặc bên lề để người dùng dễ dàng theo dõi và thực hiện theo đúng quy định của hệ thống. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
3 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm ảnh | Trong giao diện thêm thông tin sản phẩm, với các loại nhập file ảnh sẽ chỉ hỗ trợ jpg,jpeg,png. Nhưng sẽ như thế nào nếu người dùng nhập file có định dạng khác. Tôi nghĩ sẽ có một popup thông báo nhập sai định dạng file cho người dùng. Tôi có nghĩ đúng không? Xin vui lòng xác nhận | Đúng, khi người dùng nhập file với định dạng không hợp lệ, một popup cảnh báo cần được hiển thị. Điều này sẽ giúp tránh những lỗi không mong muốn và cải thiện trải nghiệm người dùng khi nhập thông tin sản phẩm. Chúng tôi sẽ xem xét triển khai tính năng này để hỗ trợ người dùng một cách tốt nhất. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
4 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm video | Trong bước thêm video cho sản phẩm, sẽ có các ràng buộc như kích thước tối đa 30Mb, độ phân giải không vượt quá 1280x1280px, độ dài 10s-60s. Nhưng sẽ thế nào nếu người dùng đăng tải một video không tuân thủ nguyên tắc trên? Tôi nghĩ ta sẽ cho phép người dùng chỉnh sửa video trực tiếp trên trang web cho phù hợp khi học đăng video lên để tăng trải nghiệm người dùng. Tôi có nghĩ đúng không? Xin vui lòng xác nhận | Đề xuất của bạn rất hữu ích. Thay vì chỉ thông báo lỗi khi tải lên video không hợp lệ, chúng tôi sẽ cân nhắc thêm tính năng cho phép người dùng chỉnh sửa video ngay trên trang web để phù hợp với các quy định về kích thước và độ dài. Điều này sẽ giúp cải thiện đáng kể trải nghiệm người dùng, đồng thời giảm thiểu các lỗi trong quá trình đăng tải. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
5 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm thông tin vận chuyển | Trong bước thêm thiết lập cân nặng & kích thước đóng gói. Sẽ thế nào nếu sản phẩm có các biến thể với kích thước, cân nặng khác nhau? Tôi nghĩ nên có option thiết lập cân nặng & kích thước cho từng phân loại. Tôi có nghĩ đúng không? Xin vui lòng xác nhận. | Đề xuất này hợp lý. Chúng tôi sẽ xem xét bổ sung tùy chọn để người dùng có thể thiết lập cân nặng và kích thước riêng cho từng biến thể sản phẩm. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
6 | Quản lý sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Xem danh sách sản phẩm | Trong màn hình danh sách sản phẩm của shop. Sản phẩm đã hiển thị các thông tin cơ bản, nhưng để tiện cho shop quản lý, nó nên được đánh giá tự động bởi hệ thông. Tôi nghĩ nên có thêm đánh giá chất lượng nội dung để đưa đánh giá sản phẩm có cần cải thiện, và cải thiện gì để bài đăng tốt hơn. Tôi có nghĩ đúng không? Xin vui lòng xác nhận. | Đồng ý, việc thêm chức năng đánh giá chất lượng nội dung sản phẩm sẽ giúp shop cải thiện bài đăng. Chúng tôi sẽ xem xét việc triển khai tính năng này. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
7 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm sản phẩm | Hệ thống đã có tính năng thêm 1 sản phẩm, nhưng sẽ thế nào nếu người dùng có hàng loạt sản phẩm cần được đăng tải nhanh chống? Tôi nghĩ nên có lựa chọn Đăng hàng loạt sản phẩm lên hệ thống. Người dùng sẽ được tải về một template và hoàn thành đúng theo mẫu template sau đó sẽ đăng lên và hệ thống xử lý tự động. Tôi có nghĩ đúng không? Xin vui lòng xác nhận | Đồng ý, tính năng này sẽ giúp người dùng tiết kiệm thời gian khi đăng hàng loạt sản phẩm. Chúng tôi sẽ xem xét bổ sung chức năng này với việc hỗ trợ template để đăng hàng loạt. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
8 | Quản lý sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Xem danh sách sản phẩm | Trong màn hình danh sách sản phẩm của shop. Mặc định một sản phẩm sẽ được hiển thị chi tiết sổ dọc xuống, bao gồm tất cả các biến thể làm cho khó nhìn. Tôi nghĩ nên có chế độ chuyển đổi sang gốc nhìn như của người mua. Hiển thị gắn gọn thông tin của 1 sản phẩm, để shop có thể xem hàng loạt các sản phẩm một cách nhanh chống. Tôi có nghĩ đúng không? Xin vui lòng xác nhận | Đồng ý, việc thêm chế độ xem gọn gàng sẽ giúp shop quản lý danh sách sản phẩm dễ dàng hơn. Chúng tôi sẽ xem xét triển khai tính năng này. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Low
9 | Quản lý sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Tồn kho sản phẩm | Hệ thống đã có tính năng tồn kho sản phẩm, nhưng hiện tại vẫn chưa có nhắc nhở tồn kho. Tôi nghĩ người dùng nên được tùy chọn bật thông báo nhắc nhớ tồn kho sản phẩm khi hạ thấp đến một mức độ nào đó để shop có thể chủ động nhập hàng. Tôi có nghĩ đúng không? Xin vui lòng xác nhận | Đồng ý, tính năng này sẽ giúp shop chủ động trong việc quản lý hàng tồn kho. Chúng tôi sẽ xem xét bổ sung chức năng nhắc nhở tùy chọn này. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium
10 | Thêm sản phẩm | SRS - Quản lý sản phẩm | 1.0 | Thêm thông tin chi tiếtsản phẩm | Trong giao diện thêm thông tin chi tiết sản phẩm. Hiện tại form thông tin đang được đặt cố định. Tôi nghĩ nó nên được linh hoạt thay đổi dựa theo ngành hàng được chọn từ bước "Thông tin cơ bản" để cho phù hợp hơn với từng loại ngành hàng. Tôi có nghĩ đúng không? Xin vui lòng xác nhận. | Đồng ý, việc thay đổi form linh hoạt theo ngành hàng sẽ giúp người dùng nhập thông tin phù hợp hơn. Chúng tôi sẽ xem xét bổ sung tính năng này để cải thiện trải nghiệm người dùng. (21130451 - Nguyễn Thị Chúc Ngân) | Open |  | Medium